## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | Lexington Square- Lot 5 | 303 days | March 05, 2025 8:00 AM | May 27, 2026 5:00 PM |  | 1
2 | Yes | Auto Scheduled | Horizontal works | 267 days | March 05, 2025 8:00 AM | April 07, 2026 5:00 PM |  | 2
3 | Yes | Auto Scheduled | Earthwork | 30 days | March 05, 2025 8:00 AM | April 15, 2025 5:00 PM |  | 3
4 | Yes | Auto Scheduled | Erosion Control | 3 days | March 05, 2025 8:00 AM | March 07, 2025 5:00 PM |  | 4
5 | Yes | Auto Scheduled | Silt Fence | 3 days | March 05, 2025 8:00 AM | March 07, 2025 5:00 PM |  | 5
6 | Yes | Auto Scheduled | Construction Entrance | 0 days | March 05, 2025 8:00 AM | March 05, 2025 5:00 PM | 5 | 5
7 | Yes | Auto Scheduled | Inlet Protection | 1 day | March 05, 2025 8:00 AM | March 05, 2025 5:00 PM | 6SS | 5
8 | Yes | Auto Scheduled | Site Grading | 27 days | March 10, 2025 8:00 AM | April 15, 2025 5:00 PM |  | 4
9 | Yes | Auto Scheduled | Rough Grading/ Clear and Grub | 10 days | March 10, 2025 8:00 AM | March 21, 2025 5:00 PM | 7 | 5
10 | Yes | Auto Scheduled | Building Pad Preparation with inspections | 12 days | March 10, 2025 8:00 AM | April 15, 2025 5:00 PM | 9 | 5
11 | Yes | Auto Scheduled | Completion of Building Pad preparations for both the buildings | 1 day | April 15, 2025 8:00 AM | April 15, 2025 5:00 PM | 10 | 5
12 | Yes | Auto Scheduled | Site Utilities | 45 days | April 28, 2025 8:00 AM | June 30, 2025 5:00 PM |  | 3
13 | Yes | Auto Scheduled | Sewer line | 5.5 days | April 28, 2025 8:00 AM | May 15, 2025 5:00 PM | 10 | 4
14 | Yes | Auto Scheduled | Storm Line | 17 days | May 07, 2025 8:00 AM | May 30, 2025 5:00 PM | 13SS | 4
15 | Yes | Auto Scheduled | Water line | 0 days | April 28, 2025 8:00 AM | May 13, 2025 5:00 PM | 14 | 4
16 | Yes | Auto Scheduled | Testing and Inspections | 13 days | May 21, 2025 8:00 AM | June 23, 2025 5:00 PM | 15 | 4
17 | Yes | Auto Scheduled | Final Grading | 5 days | June 24, 2025 8:00 AM | June 30, 2025 5:00 PM | 16 | 4
18 | Yes | Auto Scheduled | Completion of Site utilities with rough grading | 0 days | June 30, 2025 5:00 PM | June 30, 2025 5:00 PM | 17 | 4
19 | Yes | Auto Scheduled | Paving | 195 days | June 16, 2025 8:00 AM | April 07, 2026 5:00 PM |  | 3
20 | Yes | Auto Scheduled | Under ground gas and data | 7 days | June 16, 2025 8:00 AM | June 24, 2025 5:00 PM | 18FS+12d | 4
21 | Yes | Auto Scheduled | Lime Stabilization with inspections | 10 days | July 07, 2025 8:00 AM | July 18, 2025 5:00 PM | 20 | 4
22 | Yes | Auto Scheduled | 6"Heavy Duty with inspections | 167.6 days | July 21, 2025 8:00 AM | April 07, 2026 5:00 PM | 21 | 4
23 | Yes | Auto Scheduled | Completion of Paving | 1 day | April 07, 2026 8:00 AM | April 07, 2026 5:00 PM | 22 | 4
24 | Yes | Auto Scheduled | Vertical works dependencies | 166 days | August 01, 2025 5:00 PM | April 14, 2026 5:00 PM |  | 2
25 | Yes | Auto Scheduled | Building 1 - Steel shop drawing approval | 0 days | August 01, 2025 5:00 PM | August 01, 2025 5:00 PM | 26SS-15d | 3
26 | Yes | Auto Scheduled | Building 1 - Release steel | 0 days | August 22, 2025 5:00 PM | August 22, 2025 5:00 PM | 55SS-22d | 3
27 | Yes | Auto Scheduled | Building 1 Storefront shop drawings approval | 0 days | August 07, 2025 5:00 PM | August 07, 2025 5:00 PM | 28SS-7d | 3
28 | Yes | Auto Scheduled | Building 1 - Storefront release | 0 days | September 08, 2025 5:00 PM | September 08, 2025 5:00 PM | 67SS-112d | 3
29 | Yes | Auto Scheduled | Building 1 - Fire alarm final inspection | 0 days | April 14, 2026 5:00 PM | April 14, 2026 5:00 PM | 82 | 3
30 | Yes | Auto Scheduled | Building 1 - Release knox box | 0 days | March 07, 2026 8:00 AM | March 07, 2026 5:00 PM |  | 3
31 | Yes | Auto Scheduled | Building 1 - Release address sign | 0 days | March 07, 2026 8:00 AM | March 07, 2026 5:00 PM |  | 3
32 | Yes | Auto Scheduled | Building 2 - Steel shop drawing approval | 0 days | August 01, 2025 5:00 PM | August 01, 2025 5:00 PM | 26SS-15d | 3
33 | Yes | Auto Scheduled | Building 2 - Release steel | 0 days | August 22, 2025 5:00 PM | August 22, 2025 5:00 PM | 55SS-22d | 3
34 | Yes | Auto Scheduled | Building 2 - Storefront shop drawings approval | 0 days | August 27, 2025 5:00 PM | August 27, 2025 5:00 PM | 28SS-7d | 3
35 | Yes | Auto Scheduled | Building 2 - Storefront release | 0 days | September 08, 2025 5:00 PM | September 08, 2025 5:00 PM | 67SS-112d | 3
36 | Yes | Auto Scheduled | Building 2 - Fire alarm final inspection | 0 days | March 06, 2026 8:24 AM | March 06, 2026 8:24 AM | 133 | 3
37 | Yes | Auto Scheduled | Building 2 - Release knox box | 0 days | March 07, 2026 8:00 AM | March 07, 2026 5:00 PM |  | 3
38 | Yes | Auto Scheduled | Building 2 - Release address sign | 0 days | March 07, 2026 8:00 AM | March 07, 2026 5:00 PM |  | 3
39 | Yes | Auto Scheduled | Vertical works | 184 days | August 21, 2025 8:00 AM | May 27, 2026 5:00 PM |  | 2
40 | Yes | Auto Scheduled | Permit - Frisco Permit | 0 days | August 21, 2025 8:00 AM | August 21, 2025 8:00 AM |  | 3
41 | Yes | Auto Scheduled | Building 1 | 176.88 days | August 21, 2025 8:00 AM | May 18, 2026 4:02 PM |  | 3
42 | Yes | Auto Scheduled | Pier Foundation works | 7 days | August 25, 2025 8:00 AM | September 03, 2025 5:00 PM |  | 4
43 | Yes | Auto Scheduled | Pier Drilling | 7 days | August 25, 2025 8:00 AM | September 03, 2025 5:00 PM | 40FS+2d | 5
44 | Yes | Auto Scheduled | Reinforcement placing | 7 days | August 25, 2025 8:00 AM | September 03, 2025 5:00 PM | 43FF | 5
45 | Yes | Auto Scheduled | Third party Inspection | 7 days | August 25, 2025 8:00 AM | September 03, 2025 5:00 PM | 44FF | 5
46 | Yes | Auto Scheduled | Concreting | 7 days | August 25, 2025 8:00 AM | September 03, 2025 5:00 PM | 45FF | 5
47 | Yes | Auto Scheduled | Building Pad | 30 days | September 04, 2025 8:00 AM | October 16, 2025 5:00 PM |  | 4
48 | Yes | Auto Scheduled | External Form work | 1 day | September 04, 2025 8:00 AM | September 04, 2025 5:00 PM | 46 | 5
49 | Yes | Auto Scheduled | Under ground plumbing | 5 days | September 05, 2025 8:00 AM | September 11, 2025 5:00 PM | 48 | 5
50 | Yes | Auto Scheduled | Grade Beams | 16 days | September 19, 2025 8:00 AM | October 10, 2025 5:00 PM | 49 | 5
51 | Yes | Auto Scheduled | Grade Slabs | 15.4 days | September 19, 2025 8:00 AM | October 10, 2025 5:00 PM | 50 | 5
52 | Yes | Auto Scheduled | Third party Inspection | 1 day | October 07, 2025 8:00 AM | October 07, 2025 5:00 PM | 51 | 5
53 | Yes | Auto Scheduled | Concreting | 1 day | October 16, 2025 8:00 AM | October 16, 2025 5:00 PM | 52 | 5
54 | Yes | Auto Scheduled | Structural Steel | 52 days | November 19, 2025 8:00 AM | February 18, 2026 5:00 PM |  | 4
55 | Yes | Auto Scheduled | Columns and Beams Erection | 18 days | November 19, 2025 8:00 AM | December 26, 2025 5:00 PM | 53FS+14d | 5
56 | Yes | Auto Scheduled | Deck and Joist erection | 34 days | December 06, 2025 8:00 AM | February 18, 2026 5:00 PM | 55 | 5
57 | Yes | Auto Scheduled | Third party Inspection | 0 days | January 07, 2026 8:00 AM | January 07, 2026 5:00 PM | 56 | 5
58 | Yes | Auto Scheduled | Framing and Sheathing | 45 days | January 07, 2026 8:00 AM | March 10, 2026 5:00 PM |  | 4
59 | Yes | Auto Scheduled | Metal Framing | 29 days | January 07, 2026 8:00 AM | February 17, 2026 5:00 PM | 57 | 5
60 | Yes | Auto Scheduled | Sheathing and Insulation | 34 days | January 20, 2026 8:00 AM | March 10, 2026 5:00 PM | 59SS+14d | 5
61 | Yes | Auto Scheduled | Roofing | 24 days | February 17, 2026 8:00 AM | March 21, 2026 5:00 PM |  | 4
62 | Yes | Auto Scheduled | TPO Roof system as per plans | 7 days | February 17, 2026 8:00 AM | February 25, 2026 5:00 PM | 57 | 5
63 | Yes | Auto Scheduled | Standing Seam metal roof as per plans | 5 days | March 16, 2026 8:00 AM | March 21, 2026 5:00 PM | 57 | 5
64 | Yes | Auto Scheduled | Façade works | 56 days | February 20, 2026 8:00 AM | May 08, 2026 5:00 PM |  | 4
65 | Yes | Auto Scheduled | Masonry works as per plans | 39.2 days | February 20, 2026 8:00 AM | May 08, 2026 5:00 PM | 63 | 5
66 | Yes | Auto Scheduled | Doors, windows & Hardware | 72 days | January 28, 2026 8:00 AM | May 07, 2026 5:00 PM |  | 4
67 | Yes | Auto Scheduled | Aluminium Entrances& Store Front Systems | 19.8 days | February 18, 2026 8:00 AM | May 07, 2026 5:00 PM | 65 | 5
68 | Yes | Auto Scheduled | Exit Doors | 0 days | January 28, 2026 8:00 AM | April 08, 2026 5:00 PM | 67 | 5
69 | Yes | Auto Scheduled | Hardware Installation | 0 days | April 08, 2026 8:00 AM | April 08, 2026 5:00 PM | 68 | 5
70 | Yes | Auto Scheduled | Electrical | 19 days | March 17, 2026 8:00 AM | April 10, 2026 5:00 PM |  | 4
71 | Yes | Auto Scheduled | Rough Electrical with Rough -in Inspections | 0 days | March 17, 2026 8:00 AM | April 10, 2026 5:00 PM | 69 | 5
72 | Yes | Auto Scheduled | Fixtures | 0 days | April 06, 2026 8:00 AM | April 07, 2026 5:00 PM | 71 | 5
73 | Yes | Auto Scheduled | Services with Final inspections | 4 days | April 07, 2026 8:00 AM | April 10, 2026 5:00 PM | 71FF | 5
74 | Yes | Auto Scheduled | Plumbing | 63.88 days | February 18, 2026 8:00 AM | May 18, 2026 4:02 PM |  | 4
75 | Yes | Auto Scheduled | Rough Plumbing with Inspections | 0.1 days | February 18, 2026 8:00 AM | February 18, 2026 8:48 AM | 71FF+3d | 5
76 | Yes | Auto Scheduled | Final | 3 days | February 28, 2026 8:00 AM | May 18, 2026 4:02 PM | 72FF | 5
77 | Yes | Auto Scheduled | Completion of plumbing work for building 1 | 0 days | May 18, 2026 4:02 PM | May 18, 2026 4:02 PM | 76 | 5
78 | Yes | Auto Scheduled | Mechanical | 3 days | April 17, 2026 8:00 AM | April 21, 2026 5:00 PM |  | 4
79 | Yes | Auto Scheduled | Heaters Installation | 3 days | April 17, 2026 8:00 AM | April 21, 2026 5:00 PM | 72FF | 5
80 | Yes | Auto Scheduled | Fire Systems | 67 days | January 12, 2026 8:00 AM | April 14, 2026 5:00 PM |  | 4
81 | Yes | Auto Scheduled | Fire Sprinkler | 21 days | January 12, 2026 8:00 AM | April 03, 2026 5:00 PM | 63 | 5
82 | Yes | Auto Scheduled | Fire Alarm | 7 days | April 06, 2026 8:00 AM | April 14, 2026 5:00 PM | 81 | 5
83 | Yes | Auto Scheduled | Specialities | 169 days | August 21, 2025 8:00 AM | May 06, 2026 5:00 PM |  | 4
84 | Yes | Auto Scheduled | Knox Box & Address Sign | 9 days | April 24, 2026 8:00 AM | May 06, 2026 5:00 PM | 79FF | 5
85 | Yes | Auto Scheduled | Total Completion of Building 1 | 0 days | August 21, 2025 8:00 AM | August 21, 2025 8:00 AM |  | 5
86 | Yes | Auto Scheduled | Miscellaneous | 49.88 days | February 25, 2026 8:00 AM | May 05, 2026 4:02 PM |  | 4
87 | Yes | Auto Scheduled | Side walks | 10 days | February 25, 2026 8:00 AM | May 05, 2026 4:02 PM | 69 | 5
88 | Yes | Auto Scheduled | Building 2 | 169 days | August 21, 2025 8:00 AM | May 06, 2026 5:00 PM |  | 3
89 | Yes | Auto Scheduled | Pier Foundation works | 5 days | September 04, 2025 8:00 AM | September 10, 2025 5:00 PM |  | 4
90 | Yes | Auto Scheduled | Pier Drilling | 5 days | September 04, 2025 8:00 AM | September 10, 2025 5:00 PM | 43 | 5
91 | Yes | Auto Scheduled | Reinforcement placing | 5 days | September 04, 2025 8:00 AM | September 10, 2025 5:00 PM | 44 | 5
92 | Yes | Auto Scheduled | Inspection | 5 days | September 04, 2025 8:00 AM | September 10, 2025 5:00 PM | 45 | 5
93 | Yes | Auto Scheduled | Concreting | 5 days | September 04, 2025 8:00 AM | September 10, 2025 5:00 PM | 46 | 5
94 | Yes | Auto Scheduled | Buidling Pad | 11 days | September 11, 2025 8:00 AM | September 25, 2025 5:00 PM |  | 4
95 | Yes | Auto Scheduled | External Form work | 1 day | September 11, 2025 8:00 AM | September 11, 2025 5:00 PM | 93 | 5
96 | Yes | Auto Scheduled | Under ground plumbing | 5 days | September 12, 2025 8:00 AM | September 18, 2025 5:00 PM | 95 | 5
97 | Yes | Auto Scheduled | Grade Beams | 0 days | September 15, 2025 8:00 AM | September 18, 2025 5:00 PM | 96 | 5
98 | Yes | Auto Scheduled | Grade Slabs | 0 days | September 15, 2025 8:00 AM | September 15, 2025 8:00 AM | 97 | 5
99 | Yes | Auto Scheduled | Inspection | 1 day | September 22, 2025 8:00 AM | September 22, 2025 5:00 PM | 98 | 5
100 | Yes | Auto Scheduled | Concreting | 1 day | September 25, 2025 8:00 AM | September 25, 2025 5:00 PM | 99 | 5
101 | Yes | Auto Scheduled | Completion of Foundation works for building 2 | 0 days | September 25, 2025 8:00 AM | September 25, 2025 8:00 AM | 100 | 5
102 | Yes | Auto Scheduled | Structural Steel | 36 days | October 13, 2025 8:00 AM | December 09, 2025 5:00 PM |  | 4
103 | Yes | Auto Scheduled | Columns and Beams Erection | 0 days | October 13, 2025 8:00 AM | October 31, 2025 5:00 PM | 55SS+5d | 5
104 | Yes | Auto Scheduled | Deck and Joist erection | 6.4 days | October 21, 2025 8:00 AM | December 09, 2025 5:00 PM | 103 | 5
105 | Yes | Auto Scheduled | Inspection | 0 days | December 09, 2025 8:00 AM | December 09, 2025 8:00 AM | 104 | 5
106 | Yes | Auto Scheduled | Framing and Sheathing | 62 days | November 04, 2025 8:00 AM | February 17, 2026 5:00 PM |  | 4
107 | Yes | Auto Scheduled | Metal Framing | 0 days | November 04, 2025 8:00 AM | December 19, 2025 5:00 PM | 105 | 5
108 | Yes | Auto Scheduled | Sheathing and Insulation | 0 days | November 13, 2025 8:00 AM | February 17, 2026 5:00 PM | 107 | 5
109 | Yes | Auto Scheduled | Roofing | 53 days | December 12, 2025 8:00 AM | March 09, 2026 5:00 PM |  | 4
110 | Yes | Auto Scheduled | TPO Roof system as per plans | 5 days | December 31, 2025 8:00 AM | January 08, 2026 5:00 PM | 105 | 5
111 | Yes | Auto Scheduled | Standing Seam metal roof as per plans | 53 days | December 12, 2025 8:00 AM | March 09, 2026 5:00 PM | 105 | 5
112 | Yes | Auto Scheduled | Completion of Roofing for Building 2 | 1 day | March 09, 2026 8:00 AM | March 09, 2026 5:00 PM | 111,110 | 5
113 | Yes | Auto Scheduled | Façade works | 59 days | January 07, 2026 8:00 AM | March 30, 2026 5:00 PM |  | 4
114 | Yes | Auto Scheduled | Masonry works as per plans | 33.2 days | January 07, 2026 8:00 AM | March 30, 2026 5:00 PM | 112 | 5
115 | Yes | Auto Scheduled | Doors, windows & Hardware | 38 days | January 19, 2026 8:00 AM | March 11, 2026 5:00 PM |  | 4
116 | Yes | Auto Scheduled | Aluminium Entrances&Store Front Systems | 0 days | January 19, 2026 8:00 AM | February 10, 2026 5:00 PM | 114 | 5
117 | Yes | Auto Scheduled | Exit Doors | 20 days | January 28, 2026 8:00 AM | March 09, 2026 5:00 PM | 116 | 5
118 | Yes | Auto Scheduled | Hardware Installation | 2 days | March 09, 2026 8:00 AM | March 11, 2026 5:00 PM | 117 | 5
119 | Yes | Auto Scheduled | Completion of Store Front System and complete external wrap up for Building 2 | 38 days | January 19, 2026 8:00 AM | March 11, 2026 5:00 PM | 118,116,117 | 5
120 | Yes | Auto Scheduled | Electrical | 83 days | December 31, 2025 8:00 AM | April 28, 2026 5:00 PM |  | 4
121 | Yes | Auto Scheduled | Rough Electrical with Inspections | 0 days | December 31, 2025 8:00 AM | February 25, 2026 5:00 PM | 118 | 5
122 | Yes | Auto Scheduled | Fixtures | 41 days | February 27, 2026 8:00 AM | April 24, 2026 5:00 PM | 121 | 5
123 | Yes | Auto Scheduled | Services with inspections | 3 days | April 24, 2026 8:00 AM | April 28, 2026 5:00 PM | 121FF | 5
124 | Yes | Auto Scheduled | Completion of electrical work for building 2 | 0 days | April 24, 2026 5:00 PM | April 24, 2026 5:00 PM | 122 | 5
125 | Yes | Auto Scheduled | Plumbing | 95 days | December 02, 2025 8:00 AM | April 24, 2026 5:00 PM |  | 4
126 | Yes | Auto Scheduled | Rough Plumbing with Inspections | 0.09 days | December 02, 2025 8:00 AM | December 02, 2025 8:43 AM | 121FF+1d | 5
127 | Yes | Auto Scheduled | Final | 2 days | December 04, 2025 8:00 AM | April 24, 2026 5:00 PM | 122FF | 5
128 | Yes | Auto Scheduled | Completion of plumbing work for building 2 | 0 days | April 24, 2026 5:00 PM | April 24, 2026 5:00 PM | 127 | 5
129 | Yes | Auto Scheduled | Mechanical | 1 day | February 25, 2026 8:00 AM | February 25, 2026 5:00 PM |  | 4
130 | Yes | Auto Scheduled | Heaters Installation | 1 day | February 25, 2026 8:00 AM | February 25, 2026 5:00 PM | 122FF | 5
131 | Yes | Auto Scheduled | Fire Systems | 61.05 days | November 21, 2025 8:00 AM | March 06, 2026 8:24 AM |  | 4
132 | Yes | Auto Scheduled | Fire Sprinkler | 6 days | November 21, 2025 8:00 AM | March 05, 2026 8:24 AM | 130 | 5
133 | Yes | Auto Scheduled | Fire Alarm | 1 day | March 05, 2026 8:24 AM | March 06, 2026 8:24 AM | 132 | 5
134 | Yes | Auto Scheduled | Specialities | 169 days | August 21, 2025 8:00 AM | May 06, 2026 5:00 PM |  | 4
135 | Yes | Auto Scheduled | Knox Box&Address Sign | 9 days | March 16, 2026 8:00 AM | May 06, 2026 5:00 PM | 122FF | 5
136 | Yes | Auto Scheduled | Total Completion of Building 2 | 0 days | August 21, 2025 8:00 AM | August 21, 2025 8:00 AM |  | 5
137 | Yes | Auto Scheduled | Miscellaneous | 9 days | March 30, 2026 8:00 AM | April 09, 2026 5:00 PM |  | 4
138 | Yes | Auto Scheduled | Side walks | 9 days | March 30, 2026 8:00 AM | April 09, 2026 5:00 PM | 118 | 5
139 | Yes | Auto Scheduled | Land Scaping & Open space works | 59 days | March 06, 2026 8:00 AM | May 27, 2026 5:00 PM |  | 3
140 | Yes | Auto Scheduled | Irrigation as per plans for both the buildings | 14 days | March 06, 2026 8:00 AM | March 25, 2026 5:00 PM | 118FF+2d | 4
141 | Yes | Auto Scheduled | Landscaping as per plans | 15 days | May 07, 2026 8:00 AM | May 27, 2026 5:00 PM |  | 4
142 | Yes | Auto Scheduled | Open space works as per plans | 7 days | April 30, 2026 8:00 AM | May 27, 2026 5:00 PM | 141FF | 4
143 | Yes | Auto Scheduled | Completetion of Land scaping, Irrigation and open spaces | 0 days | May 27, 2026 5:00 PM | May 27, 2026 5:00 PM | 142 | 4

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units